## Product Backlog
Project Name: |  | GAM125 - Product Backlog
Arkania
Degree | Team Member (Full Name) | Team Role / Interests | Epics (Big Features)
Game Programming | Jennifer Miller | Team lead | Defines Core Funtionality, Fun Factor, & Innovation
Robotics and Embedded Systems | Anika Franklin | Team member | Epic 1: | Characters
Game Design | Garland Garner | Team member | Epic 2: | Medieval Time
|  |  | Epic 3: | Board Game
|  |  | Epic 4: | Materials/Items
|  |  | Epic 5: | Classes
ID # | Part of Epic # | User Stories (Features) | Priority # | Estimated Sprint # | Date Added | Est. Time (Hours) | Total Hours: | 45
1 | 1 | Playable Characters | 1 |  |  | 4
2 | 1 | Kingdom Encounter cards, Attack cards | 1 |  |  | 4
3 | 1 | Rules | 1 |  |  | 7
4 | 1 | Quests | 2
5 | 2 | Weapons | 2
6 | 2 | Structures | 2
7 | 2 | Maps- Board game | 1 |  |  | 6
8 | 2 | Kingdoms | 2
9 | 3 | Bases | 2
10 | 3 | Cave Systems | 2
11 | 3 | Cards- Chest tokens, Character tokens, Kingdom cards, | 2
12 | 3 | Dice-Encounter Dice, Alliance dice, | 2
13 | 4 | treasure cards planning | 1 |  |  | 3
14 | 4 | treasure cards -Medicine and ores | 2
15 | 4 | kingdom cards planning | 1 |  |  | 6
16 | 4 | treasure cards -Gold and items | 2
17 | 5 | Orcs and Goblin character cards | 1 |  |  | 6
18 | 5 | Spider character cards | 1 |  |  | 3
19 | 5 | Kobold character cards | 1 |  |  | 3
20 | 5 | Lizard character cards | 1 |  |  | 3
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100