## Product Backlog
Project Name: |  | GAM125 - Sprint Backlog
Arkania
Degree | Team Member (Full Name) | Team Role / Interests | Sprint Information
Game Programming | Jennifer Miller | Team Lead | Sprint Number:
Robotics and Embedded Systems | Anika Franklin | Team Member
Game Design | Garland Garner | Team Member | Days In Sprint:
|  |  | Sprint Dates: | 05/21/2024 - ??/??/20??
Part of ID # | Task (to-do) | Description / Notes | Assigned To (Team Member) | Est. Time (Hours) | Total Hours: | 45
1 | Playable Characters | character background | Jennifer | 4
2 | Kingdom Encounter cards, Attack cards |  | Jennifer | 4
3 | Rules | Rules | Jennifer | 7
4 | Maps -Board game |  | Garland | 6
5 | Treasure card planning |  | Garland | 3
6 | Kingdom cards planning |  | Garland | 6
7 | Orcs and Goblin character cards |  | Anika | 6
8 | Spiders character cards |  | Anika | 3
9 | Kobolds character cards |  | Anika | 3
10 | Lizards character cards |  | Anika | 3